## Implementation Plan
DORA SNI Implementation Action Plan
Reusable licensing-readiness plan. Replace role placeholders, dates and dependencies with entity facts.
Action ID | Workstream | Action | Responsible Party | Named Owner | Readiness Gate | Priority | Status | Target Date | Dependency | Deliverable / Evidence | Issue / Decision | Completion Criteria | Notes
P1 | Scope and classify | Confirm DORA scope, SNI, microenterprise, group, services, client assets/payments, TLPT and target dates | Legal / Compliance |  | Before application | Critical blocker | Not started
P2 | Map functions and technology | Populate D04 and initial D10; identify critical functions, assets, data, providers and dependencies | Management / ICT |  | Before application | Critical blocker | Not started
P3 | Assess risk | Populate D03; approve tolerance, treatments and open decisions | Management / Compliance |  | Before application | Critical blocker | Not started
P4 | Tailor and approve documents | Tailor D01/D02/D05/D06/D08/D09/D12 and align roles/definitions | Legal / Management |  | Before application | Critical blocker | Not started
P5 | Remediate providers | Complete D11 packs, contract gaps, subcontracting, concentration, exits and notifications | Legal / Provider Owner |  | Before authorisation | Critical blocker | Not started
P6 | Implement and evidence controls | Access, configuration, monitoring, backup, JML, incidents and D14 evidence | ICT / Management |  | Before launch | Critical blocker | Not started
P7 | Train, test and assure | Board/staff training, tabletop, restore test, security tests and D13 readiness review | Management / Compliance / Audit |  | Before authorisation | Critical blocker | Not started
D01 | Deliverable tailoring | Tailor, validate, approve and implement D01 — DORA Governance & Simplified ICT Risk Management Framework | Document Owner |  | Before authorisation | High | Not started
D02 | Deliverable tailoring | Tailor, validate, approve and implement D02 — Information Security & ICT Operations Policy | Document Owner |  | Before authorisation | High | Not started
D03 | Deliverable tailoring | Tailor, validate, approve and implement D03 — ICT Risk Register | Document Owner |  | Before authorisation | High | Not started
D04 | Deliverable tailoring | Tailor, validate, approve and implement D04 — Critical Functions, Assets & Dependencies Register | Document Owner |  | Before authorisation | High | Not started
D05 | Deliverable tailoring | Tailor, validate, approve and implement D05 — ICT Business Continuity, Response & Recovery Plan | Document Owner |  | Before authorisation | High | Not started
D06 | Deliverable tailoring | Tailor, validate, approve and implement D06 — ICT Incident Management & DORA Reporting Procedure | Document Owner |  | Before authorisation | High | Not started
D07 | Deliverable tailoring | Tailor, validate, approve and implement D07 — ICT Incident Register | Document Owner |  | Before launch | High | Not started
D08 | Deliverable tailoring | Tailor, validate, approve and implement D08 — Digital Operational Resilience Testing Programme & Reports | Document Owner |  | Before authorisation | High | Not started
D09 | Deliverable tailoring | Tailor, validate, approve and implement D09 — ICT Third-Party Risk Management Procedure | Document Owner |  | Before authorisation | High | Not started
D10 | Deliverable tailoring | Tailor, validate, approve and implement D10 — DORA Register of Information | Compliance / Provider Owner |  | Before authorisation | High | Not started
D11 | Deliverable tailoring | Tailor, validate, approve and implement D11 — ICT Provider Compliance Pack | Document Owner |  | Before authorisation | High | Not started
D12 | Deliverable tailoring | Tailor, validate, approve and implement D12 — ICT/DORA Training Programme & Records | Document Owner |  | Before authorisation | High | Not started
D13 | Deliverable tailoring | Tailor, validate, approve and implement D13 — Internal Audit & Simplified Framework Review Pack | Document Owner |  | Before authorisation | High | Not started
D14 | Deliverable tailoring | Tailor, validate, approve and implement D14 — ICT Control Evidence Register | Document Owner |  | Before authorisation | High | Not started

## Decisions & Assumptions
Decisions & Assumptions Log
Do not bury unresolved scope or proportionality decisions in narrative.
Decision ID | Topic | Assumption / Question | Options | Recommendation | Decision | Owner | Due | Impact / Documents | Evidence / Approval

## Annual Calendar
Suggested Annual DORA Calendar
Tailor frequencies to risk, firm size and approved policies.
Period | Activity | Deliverable | Owner | Evidence | Escalation / Decision | Status
Monthly | Incident trend and risk updates | D03/D07 | [ROLE] | Registers / report | Material changes | Not started
Quarterly | Access, vulnerability/patch and provider monitoring | D02/D09/D14 | [ROLE] | Reviews / reports | Overdue critical items | Not started
Quarterly | Management-body ICT dashboard | D01 | [ROLE] | Board pack / minutes | Risk and resources | Not started
Semi-annual | Criticality, asset and dependency reconciliation | D04 | [ROLE] | Approved inventory review | Changes / gaps | Not started
Annual | Continuity tabletop and restore test | D05/D08 | [ROLE] | Test reports | Findings / RTO/RPO | Not started
Annual | DORA training programme | D12 | [ROLE] | Attendance / assessments | Completion / effectiveness | Not started
Annual | Critical-provider review and exit walk-through | D09/D11 | [ROLE] | Provider pack / test | Contract / concentration risk | Not started
Annual | Risk-based internal audit / assurance | D13 | [ROLE] | Audit report | Critical findings | Not started
Annual / trigger | Simplified-framework review report | D13 | [ROLE] | Article 41 report | Board approval | Not started